# Appendix A. Playbook for the next regulation

### Step 1: Agree scope and the first review

Confirm the legal area, exclusions, expected output and required columns, including whether schema-fit analysis is needed. Set an early checkpoint around one fully extracted and structured regulation, so the approach can change before a large investment. Two weeks is a suggested interval, not an established estimate.

### Step 2: Find, prioritize and read

List the relevant laws and issuing authorities with official links. Prioritize regulations behind frequent operational mistakes and check overlap with existing extraction. Read the whole regulation before structuring it: identify definitions, cross-references and chapters that apply to different groups, and record any proposed skips with reasons.

### Step 3: Prepare the register before starting

Reuse the established layout and add all anticipated columns before a large batch. In our work, columns added later forced us to revisit earlier rows.

- Traceability fields: source, paragraph URL, chapter, paragraph, original text, extraction date, reviewer, and source version or latest amendment. Keep the visit date separate from the source version.

- Analytical fields: Scope, Condition, Demand, verification, normative type, action verb, data dependencies and any requested schema-fit notes.

- Use paragraph-specific Lovdata links. Paste links and dates rather than drag-filling them, because autofill can silently change values.

- Use controlled lists for normative types, action verbs, and scope types. Our register ended with 132 action verbs, 63 of them used only once, and capitalization variants such as Shall Not and Shall not. Add new terms deliberately and tell the team.

### Step 4: Extract with agreed splitting rules

Copy the original wording exactly, correcting only capture errors such as headings attached to body text or broken lettered lists. Proposed splitting conventions:

- Give separate duties their own rows while keeping the common paragraph reference.

- Keep required document contents together unless timing or responsibility differs, while making each element checkable.

- Show alternatives as separate rows only if their group and the permitted choice stay explicit.

- Keep exceptions with the duties they modify, and mark definitions as definitions.

### Step 5: Structure and test actionability

Fill in Scope, Condition, Demand and verification, classify the normative type and action verb, and record the data needed to identify the population, establish applicability, and assess compliance. Write demands in plain English beside the source, keeping significant Norwegian terms in brackets, for example sound (forsvarlig). Writing a demand often reveals another necessary split; add the row and recheck its neighbors. Leave unresolved interpretations visible rather than assigning precise-looking values.

### Step 6: Check the batch

- Coverage: compare the register with the regulation’s contents, so every provision is extracted or excluded with a reason.

- Consistency: have a second person review near-duplicate verbs and inconsistent scope or trigger terms.

- Context: follow cross-references and check which provisions define or qualify each row.

- Interpretation: flag qualitative wording and urgency terms for legal review before product logic relies on them.

### Step 7: Hand over

A reviewable handover contains the agreed scope, columns and splitting rules; a prioritized source list; paragraph links and versions; the untouched original text and completed analytical fields; explained exclusions; and visible interpretation flags and second-person checks. Plan time for reading, cross-references, and repeated splitting, because each caused substantial rework in our exercise.